## Table 1 (Data Exerpt)
Work type (WBS) | Risk Category | Risk | Risk factor
Shotcrete Work | Construction | Arch formation difficulty | Long pouring time
|  | Cost increase due to excessive use of shotcrete material | Occurrence of overburrow
|  | Insufficient secondary support | Over pouring of shotcrete
|  | Defective shotcrete attachment | The thickness of one casting is thick (within 100mm) Foreign matter exists on the surface of the 1st shotcrete
Insufficient cleaning of the pouring surface before construction (failure to remove floating stones and pumice stones, etc.)
|  | Collapse | Shotcrete pouring delay
|  | Environmental problems | Insufficient rebound material treatment
Environmental problems arise due to inability to separate waste from shotcrete sealing
| Safety | Occupational accidents of workers | dust penetration into human body
Overloaded connections due to clogged shotcrete nozzles
| Technical | Defective shotcrete attachment | Lack of steel fiber content and length
Failure to establish appropriate drainage measures for the water generating section
Poor quality of quick payment
|  | Insufficient shotcrete strength | Poor aggregate granularity
|  | Increased shotcrete disposal cost | Increased rebound
Defective shotcrete material (sand with a lot of soil, problems with quick fixing, etc.)
Non-compliance with shotcrete placement angle

## Table 2 (Entities and relation)
Category | Entity and Relationship Type | Number | Total
Entity | Project name (NATM: Tunnel) | 1
| Work Type (wbs) | 15
| Risk (risk) | 142
| Risk factor (riskfactor) | 369 | 527
Relationship | has_work_type | 15
| has_risk | 142
| has_riskfactor | 369 | 526

## Table 3 (TRisKG Evaluation Q)
Used Case | Cypher query
1 | match(n) return(n)
2 | match(n:Tunnel)-[:has_work_type]->(m:wbs) return n,m
3 | match(n:wbs{name:"Geotechnical Investigation"})-[:has_risk]->(m:risk) return n,m

## Table 4 (validation result)
Training Set
S/N | Natural language questions (Validation set) | Generated Cypher query
1 | List the risk category associated with the tunnel project? | match (n:risk) return distinct n.riskcategory as response
2 | What are the risk factors of "Lining" of the tunnel project? | match(n:wbs{name:"Lining"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response
3 | How many risks are in the project? | match(n:risk) return count(n) As response
4 | List risks associated with the "Geotechnical Investigation" of the tunnel project. | match(n:wbs{name:"Geotechnical Investigation"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response
5 | What are the risk of "Excavation" of the tunnel project? | match(n:wbs{name:"Excavation"})-[:has_risk]->(m:risk) return m.name As response

## Table 5 Accuracy results
| No of Question (n) | Correct queries generated (nac) | Incorrect queries generated | Accuracy
Validation set | 5 | 5 | 0 | 1
Test set | 30 | 28 | 2 | 0.933

## (Testing Result)
S/N | Natural language questions (Test set) | Generated Cypher queries | Remark
1 | What are the risks associated with geotechnical investigation of the tunnel project? | match(n:wbs{name:"Geotechnical Investigation"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
2 | List the risk factors of Excavation in the tunnel project. | match(n:wbs{name:"Excavation"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
3 | Count the number of risks in the project. | match(n:risk) return count(n) As response | Correct
4 | What are the risk category associated with the tunnel project? | match (n:risk) return distinct n.riskcategory as response | Correct
5 | How many risk category is associated with the tunnel project? | match (n:risk) return count(distinct n.riskcategory) as response | Correct
6 | What are risks associated with the Rock bolting of the tunnel project? (with full stop error) | match(n:wbs{name:"Rock bolting"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
7 | How many are risks associated with the Geotechnical Investigation of the tunnel project. | match(n:wbs{name:"Geotechnical Investigation"})-[:has_risk]->(m:risk) return count(m) As response | Correct
8 | What are the risk factors of Drain in the tunnel project? | match(n:wbs{name:"Drain"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
9 | List risks associated with the water roofing of the tunnel project. | match(n:wbs{name:"Waterproofing"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Incorrect
10 | What are the risks associated with the Water Proofing of the tunnel project? | match(n:wbs{name:"Water Proofing"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
11 | How many risks are associated with the water proofing of the tunnel project? | match(n:wbs{name:"Water Proofing"})-[:has_risk]->(m:risk) return count(m) as response | Correct
12 | List the risk factors of Formwork in the tunnel project? | match (n:wbs{name:"Formwork"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
13 | What are the risks of Formwork in the tunnel projec? | match (n:wbs{name:"Formwork"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
14 | What are the risks of Formwork in the tunnel project | Error | Incorrect
15 | Count the risks of Formwork in the tunnel project | match(n:wbs{name:"Formwork"})-[:has_risk]->(m:risk) return count(m) As response | Correct
16 | What are the risk factors of Auxiliary Facilities in the tunnel project? | match(n:wbs{name:"Auxiliary Facilities"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
17 | List the risks of auxiliary facilities in the tunnel project. | match (n:wbs{name:"Auxiliary Facilities"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
18 | What are the risks of Instrumentation in the tunnel project? | match(n:wbs{name:"Instrumentation"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
19 | Count the risks of Instrumentation in the tunnel project. | match(n:wbs{name:"Instrumentation"})-[:has_risk]->(m:risk) return count(m) As response | Correct
20 | Identify the risk factors of Steel Pipe Multi-stage Grouting in the tunnel project? | match(n:wbs{name:"Steel Pipe Multi-stage Grouting"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
21 | Identify the risks of Steel Pipe Multi-stage Grouting in the tunnel project. | match (n:wbs{name:"Steel Pipe Multi-stage Grouting"})-[:has_risk]->(m:risk) return "Risk: "+ m.name + " - "+ "Risk Category: " + m.riskcategory As response | Correct
22 | Count the risks of Steel Pipe Multi-stage Grouting in the tunnel project. | match (n:wbs{name:"Steel Pipe Multi-stage Grouting"})-[:has_risk]->(m:risk) return count(m) as response | Correct
23 | List risks associated with the Gang Gates and Retaining Walls of the tunnel project. | match (n:wbs{name:"Steel Pipe Multi-stage Grouting"})-[:has_risk]->(m:risk) return count(m) as response | Correct
24 | How many risk factors are s associated with the Gang Gates and Retaining Walls of the tunnel project. | match (n:wbs{name:"Gang Gates and Retaining Walls"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return count(l) as response | Correct
25 | What are the risk factors are s associated with the Gang Gates and Retaining Walls of the tunnel project? | match (n:wbs{name:"Gang Gates and Retaining Walls"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct
26 | How many risks of Drain are in the project? | match (n:wbs{name:"Drain"})-[:has_risk]->(m:risk) return count(m) As response | Correct
27 | Count the risks of Drain in the tunnel project? | match(n:wbs{name:"Drain"})-[:has_risk]->(m:risk) return count(m) As response | Correct
28 | List the risks of Drain in the tunnel project? | match (n:wbs{name:"Drain"})-[:has_risk]->(m:risk) return m.name + " - " + " Risk Category: " + m.riskcategory as response | Correct
29 | Count the risks of Common area in the tunnel project. | match(n:wbs{name:"Common area"})-[:has_risk]->(m:risk) return count(m) As response | Correct
30 | What are the risk factors of Instrumentation in the tunnel project? | match (n:wbs{name:"Instrumentation"})-[:has_risk]->(m:risk)-[:has_riskfactor]->(l:riskfactor) return "Risk: "+ m.name + " - Risk Factor: " + l.Riskfactor As response | Correct