## Excavation
Work type (WBS) | Risk Category | Risk | Risk factor
Excavation (NATM tunnel) | Construction | Increased vertical (horizontal) strain | Heaven (Tunnel Ceiling) Deformation
Adjacent to the crusher
Sidewall deformation
Excessive displacement
Tunnel subsidence
Excessive internal displacement
|  | Collapsing | Crushing zone, progressive overburrowing
|  | (tunnel collapse, subsidence) | Insufficient coping with rapid changes in membrane lipids
Unsecured bearing capacity of existing bedrock
Unsecured safety of support materials (shotcrete, rock bolts, steel supports)
Non-compliance with design excavation site
Appearance of abnormal geologic zone and occurrence of water
|  | Collapse of the posterior membrane | Insufficient rear wall lock bolt and support work
|  | Economic loss due to under-excavation and over-excavation | Excessive use of explosives
survey error
Failure to comply with the proper amount of gunpowder
Non-compliance with design excavation site
Joint, fault zone impact
|  | Cost increase due to drilling alignment error | Move the location of the survey datum point (insufficient confirmation)
|  | Economic loss due to deterioration of blasting efficiency | Insufficient coloring work, many joints and wide gaps
| Management | Damage to surrounding structures (roads, buildings, underground pipes, utility poles, etc.) | too much charge
Vibration value exceeded during blasting
Inadequate investigation of underground facilities
Excess displacement during excavation
|  | Damage to surrounding structures (roads, buildings, underground pipes, ground poles, etc.), sinkholes | groundwater level drop
Groundwater runoff during excavation
Lowering of the groundwater level in urban low-depth tunnels
Insufficient groundwater layer reinforcement, non-treatment of water during drilling
|  | Possibility of civil complaints for damage to fixed-temperature facilities such as neighboring houses and barns, delay in construction | Blasting noise and vibration effects
Excessive charge
|  | Risk of falling after excavation and before support installation | Lack of design and judgment according to rock quality (blasting pattern, reinforcement method, etc.)
Risk of falling until the first shotcrete is poured
Insufficient clean up of dead ends
|  | Delayed construction period | Calculation of appropriate time considering excavation pattern and recent blasting permission time
(Types 4 to 6 are between 7:00 and 19:00 when 2 blasts are performed per day, and types 1 and 3 are finished between 7:00 and 11:00 the next day when 2 blasts are performed per day. increase permit time)
Rocky non-uniform section
Excavation method change and rock determination
| Safety | Worker electric shock | Jumbo Drill Temporary Wire Leakage Current
|  | Worker trapping, conflict | Chajinka unskilled person malfunction
pumice stone removal
close-up work
Poor visibility due to dust after blasting
|  | Occupational accidents related to workers' diseases | Poor working conditions in the pit due to gas and dust after blasting
|  | Fire | Concern about fire due to blasting during tunnel excavation
|  | Explosion | Risk of explosion from striking residual unexploded gunpowder
|  | Charging car conduction | Ground weakening (soft ground)
|  | Car overturn accident | Steep slope of sand pit material transport route
| Technical | Shaft collapse | Non-compliance with construction procedures such as chain block installation during sand pit lining work

## Support treatment
Work type (WBS) | Risk Category | Risk | Risk factor
Ssupport treatment | Management | Air delay due to earthwork flow imbalance | Disruptions in the selection of adjacent landfill areas or sato sites
Additional quantity due to over-excavation
When rock filling is used, additional work types for rock filling are generated.
|  | Damaged dump truck cover and rockfall | Overloading/Unloading
|  | Dump overturning in case of prop failure | Loading box jam due to excessive load size,
Poor ground conditions at the landing site
Traffic damage due to speeding and overloading
| Safety | Safety accident | Fall due to poor loading and overloading during propulsion transportation using buckets
Fall due to non-execution of workplace control during bucket movement and rotation using a crane
Fire due to overheating of dump truck and loading equipment in tunnel
Fall due to wire rope breakage during lifting with a crane
Overturning and narrowing of running vehicles due to lack of illumination and poor zoning of movement lines
Accidents occur when moving workers with upper supports
Equipment narrowing during loading and unloading
Unsecured safety due to increased driver fatigue
In the case of a railway tunnel with a small cross-sectional width, the dump truck has to come out backward when handling the support, so there is a risk of colliding and colliding with workers.
Collision with other equipment and workers due to speeding in tunnels and construction roads
Risk of collision and suffocation with nearby workers due to narrow space during load loading work
| Construction | Waste environmental issues | Difficulties in securing a site for a temporary stockyard in the complex
Mixed with shotcrete repellent material and taken out
Shotcrete is mixed with the blasting stone during buckling, causing environmental issues.
Noise and dust generated due to damage caused by the support vehicle
|  | Increase in economic loss and cost (division, waste disposal) | Consideration of equipment combination considering transport distance and support size
Addition of tent installation cost for separating shotcrete classified as waste
Excavation rock transport required
Cycle time increase due to unsecured stocking
Due to the shotcrete rebound, it is mixed in the holding force when excavating the lower half
Increase in noise, vibration and cycle time due to breakdown
|  | Additional yard storage permits and increased yard storage costs | In the case of a long tunnel, a separate storage yard is required

## Shotcrete
Work type (WBS) | Risk Category | Risk | Risk factor
Shotcrete Work | Construction | Arch formation difficulty | Long pouring time
|  | Cost increase due to excessive use of shotcrete material | Occurrence of overburrow
|  | Insufficient secondary support | Over pouring of shotcrete
|  | Defective shotcrete attachment | The thickness of one casting is thick (within 100mm) Foreign matter exists on the surface of the 1st shotcrete
Insufficient cleaning of the pouring surface before construction (failure to remove floating stones and pumice stones, etc.)
|  | Collapse | Shotcrete pouring delay
|  | Environmental problems | Insufficient rebound material treatment
Environmental problems arise due to inability to separate waste from shotcrete sealing
| Safety | Occupational accidents of workers | Dust penetration into human body
Overloaded connections due to clogged shotcrete nozzles
| Technical | Defective shotcrete attachment | Lack of steel fiber content and length
Failure to establish appropriate drainage measures for the water generating section
Poor quality of quick payment
|  | Insufficient shotcrete strength | Poor aggregate granularity
|  | Increased shotcrete disposal cost | Increased rebound
Defective shotcrete material (sand with a lot of soil, problems with quick fixing, etc.)
Non-compliance with shotcrete placement angle

## Formwork
Work type (WBS) | Risk Category | Risk | Risk factor
Form work | Construction | Formwork transformation | Stress concentration on the right leg
Formwork transverse hook not fastened
Delayed installation of steel girders, insufficient maintenance of the arch shape due to severe irregularities in the original ground
|  | tunnel deformation | Occurrence of section where steel support is not installed due to excessive excavation site
|  | lower support effect | Construction is difficult by water
Structural instability due to poor bolting connection between upper and lower halves
|  | Decreased support effect (separation behavior) | H-beam support member shotcrete casting creates a gap on the back side
|  | Steel support beam deformation and damage | Poor support member connection
|  | Unexploded strong beam linear mismatch | Insufficient shotcrete thickness around Gangjibo (decreased durability)
|  | dorsal co-occurrence | Too much quick-setting shotcrete
|  | Strong support deflection | Decreased ground support capacity
| Safety | Formwork Falling Accident | Material lifting rope peeling off
|  | worker safety accident | Support fall accident during support installation worker's work
Collision with workers due to falling support materials while transporting support materials
|  | Strong support conduction occurs | Insufficient support and excessive weight
|  | Strong support overturning and subsidence | Poor support
| Technical | decrease in durability | Difficulty in securing internal holes and reinforcing bar coating due to support material deformation or curvature error
|  | Strong support movement or warping occurs | Installation error occurs when tunnel auxiliary construction method (pipe loop, pore pulling) is performed in parallel
| Design | Air delay due to type change | Produce new types when changing types according to cancer determination during excavation
|  | Sunk cost | Pre-prepared materials are not required when changing the type due to cancer determination during excavation
|  | Suspension of construction due to the need for reinforced steel support | If the ground is worse than the design

## Rock bolt
Work type (WBS) | Risk Category | Risk | Risk factor
rock bolt | Construction | Unable to install rock bolt | Excessive groundwater runoff
Collapse of drilling hole in poor ground
|  | Fastening loosening due to excessive stress caused by blasting vibration, etc. | Fastening with a force exceeding the yield strength
|  | lower support effect | Flowing down of the fixing material of the ceiling rock bolt
Rock bolt preload is not secured due to blasting without sufficient curing time for rock bolt grouting
|  | increase in construction cost | Excessive injection of mortar during crack construction
|  | lack of support | poor construction
| Management | Damaged waterproof sheet | Risk of damage to the waterproof sheet due to not removing the steel wire for construction confirmation
| Safety | Worker constriction, collision, accident, damage | Falling to the Rockbolt Workbench with overloaded material
During the lifting of the rock bolt, it fell due to poor lifting equipment and working methods.
Damage to workers due to lack of installation during rock bolt pull-out test
Falling due to the weight of the rock bolt during construction of the rock bolt, and fear of collision with workers at the bottom
Fall due to self-weight, fear of collision with lower workers
When loading rock bolts into a charging car, workers may fall by opening the door of the charging car and loading them.
In order to shorten the construction period, after excavating the second stage, the rock bolt is installed at once, and there is a risk of falling
|  | Safety accident | Injuries during rock bolt insertion and grouting work
Falling when inserting and grouting rock bolts at the top end
Safety accidents due to plastic fragments when using resin
Safety accident risk due to rock bolt filling material selection
It is difficult to construct the design length because it is difficult to construct the rock bolt with the pumice stone inside the hole diameter.
| Technical | Reduced Rockbolt Effect | Insufficient adhesion to the shotcrete surface of the acupressure plate due to not considering the direction of joint
|  | Poor fixation of rock bolt | Shoulder and hem
Fixing material dripping
Difficulty confirming settlement
Number of drilled holes inside the drilled hole
|  | Policy maker (mortar) quantity increase | Excessive joints
Fault fracture zone appearance
Groundwater runoff
|  | lack of support | Sufficient rock bolt length, non-standard construction

## Lining
Work type (WBS) | Risk Category | risk | risk factor
lining | construction | Cracks at the top end | Difficulty in injecting ready-mixed concrete at the top end
Difficulty compacting concrete
Poor mix
Underground water occurs due to damage to the waterproofing membrane
|  | leak | Underground water leakage due to water pressure in the lining due to damage to the waterproof membrane
Split casting of joint wall
Damage to the waterproof membrane when assembling rebar
Poor construction of water stop plate
|  | Longitudinal cracks at the ceiling, lining cracks and damage | lining back subsidence
Long-term hydraulic load on the lining due to poor water pressure relief in the drainage tunnel
Cracks in mass concrete in cross-sectional tunnel section
Reconstruction due to poor interface in subsequent processes (railway system, road disaster prevention)
Shrinkage and non-compliance with installation spacing and depth of construction joints
Construction after convergence of main beam displacement
Insufficient vibration during casting and cold joint with insufficient spacing
Water pressure is generated in the lining
|  | additional cost | Use of a vertical car lift, cost incurred for movement within the tunnel (mixer truck transportation)
Transport cost cannot be applied when supply materials are contracted (mixer truck transport)
Face grinding after construction of lead haunch section
Defective finish of the connection part due to separate casting of the lining lead haunch part
Face grinding cost due to defective lining surface and damage to lining form
|  | Elution water generation | Excessive water generation
Problems with securing concrete attachment, strength and thickness
| safety | Occurrence of accidents, worker entrapment and collision (work from high places, falling objects, equipment malfunction, leakage current, excessive operation, working environment, casting vehicle, formwork opening, high temperature curing management, equipment malfunction, material and equipment fixing, equipment management, scaffolding installation management, Material movement management, scattering dust, use of defective materials) | Fall during setting work at the top of the form for lining casting work
Risk of falling during work such as welding the top of the lining
Falling during movement for assembling the outer foam of the opening lining
Fall due to failure to install handrails on top of rebar bogie in rebar reinforcement section
Falls while installing a workbench due to workers not wearing seat belts
Falls during work due to failure to install safety railings at the end of the rebar workbench
Falling while going up and down the rebar workbench without lifting facilities
Fall when constructing the lining form corner
Accident of operator falling objects passing through the central passage due to material falling between the treads inside the truck.
Rebar lifting line Falling of rebar being lifted due to breakage of lifting rope
Collision and fall due to vibration of rebar during lifting work with 1 rope hanger
Collision with a forklift moving backwards due to the lack of a warning light on the rear of the forklift
During lifting of rebar, the rope fell off while lifting the rebar due to the failure to install the release device on the hook.
Electric shock while cutting and bending rebar with a rebar processor
Pain in the neck and back as a result of working toward the ceiling (musculoskeletal disorders)
When installing and dismantling the rebar workbench, overturning and collapse due to lack of understanding of work order in advance
Fall due to excessive gap between the platform of the bogie and the tunnel wall
Bronchi damage due to scattering dust during lining foam sanding
Conduction/collapse due to the use of materials that are ineligible for rebar lending
Workers fall and slip due to poor material arrangement of lining foam stairs and work scaffolding
Risk of electric shock and fire during lining foam welding and fusing work
Danger due to fire and lack of oxygen during curing using a hot air fan in winter
Nearby workers stabbed by rebar during rebar placement
Optic nerve damage as rebar powder gets into the eye while assembling rebar toward the ceiling
In an inclined shaft, a steel workbench rolls on a slope and collapses due to external collision.
When assembling the harness form, be careful of being stabbed by the protruding reinforcing bars on the harness side
Traffic jam accident due to failure to place a signalman and failure to install a vehicle stopper while the concrete mixer truck is reversing
Fall accident due to failure to install inspection window opening cover during lining placement
Workers are trapped due to malfunction due to foot switch cover not being installed during cutting work for rebar assembly
Constriction accident due to insufficient fixation of the rebar in the slope section
Risk of damage/collapse due to non-compliance with formwork structural review and arbitrary changes
Collapse due to non-compliance with scaffolding structural review and non-compliance with assembly order
Fall due to poor tethering during handling, unloading or transportation of reinforcing bar materials
When the workbench is moved, the worker falls due to movement while moving while the worker is riding on the upper part
Concerns about collision and narrowing when remicon vehicle reverses
|  | fire | Risk of electric shock and fire during lining foam welding and fusing work
Danger due to fire and lack of oxygen during curing using a hot air fan in winter
| Technical | architectural limits | Unsecured construction limits

## Waterproof
Work type (WBS) | Risk specifics | Risk | Risk factor
Waterproof | Construction | Leakage | Poor welding of waterproof paper at connection part
Bad culvert connection at the bottom
No air test conducted on the connection part of the anchor to prevent sagging of the rebar
Connection part air test not conducted
Damaged waterproof sheet during reinforcement work
Poor welding of waterproof sheet joints
Torn waterproof sheet during rebar work
Poor connection between construction joint and waterproof sheet
Leakage due to lack of waterproofing membrane overlapping
Leakage due to poor connection of waterproof membrane longitudinal drain pipe
Watertight plate damage due to rebar assembly and rebar fixed anchor construction
NATM-Cut Tunnel Joint
Effect of the surrounding groundwater level if waterproofing quality is not secured
|  | Accidents caused by insufficient surface clearance in the tunnel | Induced cracks in the lining due to damage to the waterproofing film, inability to secure the lining coating
|  | Sagging of waterproof paper | Installation of shotcrete waterproofing fixing device at regular intervals
|  | Dropped after installation of tunnel waterproofing membrane | Tunnel strong wind inflow, insufficient number of end connection fixing facilities installed
|  | Waterproof membrane damage | Shotcrete surface has severe irregularities, damage during construction of reinforcing bars and formwork
|  | Damaged waterproof sheet | Damage when installing lining foam
When the lining is placed, the waterproof sheet is torn due to the weight of the concrete
Tearing by shotcrete protrusions
Torn due to lack of rockbolt head trim
| Safety | Accidents, damages (due to high-place work, excessive movement, working environment, working conditions, welding work, material falling, collision, etc.) | Pain in the neck and back as a result of working toward the ceiling
Lower back pain due to excessive movements such as moving up and down the waterproof seat cart
Pull up the waterproof sheet onto the workbench and fall due to the weight of the sheet member, collision, etc.
When going up and down the worktable, a fall accident occurred due to slipping on the stairs due to insufficient illumination
Collision with a bogie by a vehicle that moves underneath the bogie, such as an excavator
In the case of an inclined shaft, the waterproof work platform rolls down the slope and collapses due to external impact.
Worker's falling object accident passing through the central aisle due to material falling between the internal scaffolding of the bogie
Worker collision due to falling upper material while moving work cart
When installing and dismantling the waterproof workbench, overturning and collapsing due to unlearned work order in advance
Burns during fusion welding of waterproof sheet
Concerns about loosening and deformation of member connections due to damage accumulated during movement of the work cart due to irregularities in the floor, poor inclination of the upper foot of the cart
Fall/collapse due to the use of unqualified materials for the waterproof bogie
Fall due to excessive gap between the platform of the bogie and the tunnel wall
Electric shock accident due to use of outdated welding machine and failure to install electric shock arrestor
Fall while working on the waterproof sheet at the top of the waterproof cart
Falls while installing a workbench due to workers not wearing seat belts
Fall while lifting the waterproof sheet to the top of the work bench
Stumble and fall while forcibly working at the end of the workbench
Electric shock accident due to use of outdated welding machine and failure to install electric shock arrestor
|  | Fire | Fire occurred during welding/cutting work around the area after installing the waterproof sheet
Waterproof sheet fire due to overheating of bonding equipment
| Management | Damaged waterproof sheet | Tear due to foreign matter of shotcrete (nail, fixed iron, etc.)
Difficulty in repairing damaged parts
It is difficult to check the joint condition of the damaged repair part
Micro damage cannot be confirmed
Damage caused by fixtures when fixing the waterproof sheet
Carelessness when assembling the lining steel formwork
| Technical | Poor connection of waterproof sheet | Improper junction temperature
Difficulty in identifying defective joints
Improper connection speed
Insufficient joint spacing (insufficient joint length)
Poor connection between waterproof sheet and non-woven fabric

## Drain
Work type (WBS) | Risk specifics | Risk | Risk factor
Drain | Construction | Runoff to the back groundwater lining | Insufficient induction drainage before waterproofing work
|  | Leakage at construction joints | Construction joints caused by separate casting
|  | clogged drain | Inflow of foreign substances due to negligence during construction
|  | roadbed uplift | drainage water pressure
|  | Possibility of uplift on the pavement surface due to uplift | Water reservoir in the lower part of the geologic zone
|  | Subgrade separation and deformation | poor drainage
|  | Ceiling subsidence due to groundwater level drop | overdrain
| Management | Damaged packaging | Poor drainage of the bottom outlet
| Safety | safety accident | Risk of falling when working at height
| Technical | Water accumulation occurs due to the difference in the depth of the culvert depending on the type of excavation (ex. invert section, general section, etc.) | design error

## Common Area
Work type (WBS) | Risk specifics | Risk | Risk factor
common area | Safety | Collapses when used as an emergency evacuation passage | lack of rigidity
|  | Electric shock accident due to non-use of machinery and equipment by the 2nd division research team | Leakage current, grounding, earth leakage breaker not installed
|  | Risk of falling accidents due to poor installation of worker passageways | floor irregularities
Accidents caused by high-speed rotating equipment
|  | Eye damage from residual concrete fragments | Insufficient safety measures during sanding of utility tunnel formwork
| Technical | Separation and level difference on the mounting surface of the common hole lid | Defective joint lid mounting surface
| Construction | Poor fixation of old and new joints | Excessive divisional pouring of utility ducts
|  | Crack occurrence | No cutting

## Gang gates and retaining walls
Work type (WBS) | Risk specifics | Risk | Risk factor
Gang gates and retaining walls | Safety | Gang gate-slope confined space disease occurrence | Lack of oxygen such as asphalt coating work
| Construction | Shaft slope collapse and loss | After the installation of the shaft gate, the rear slope is neglected
Insufficient height of parapet or length of open pit in case of heavy rain
Continuous loss of slopes in the shaft section due to rain
Insufficient securing of drainage on the side of the shaft
|  | Retaining wall sliding and ground subsidence | Insufficient filling of the back of the retaining wall
|  | retaining wall collapse | Insufficient infiltrate treatment facility in retaining wall causes increase in backside earth pressure
Increase in active soil pressure on retaining walls due to increase in volume of frozen soil in winter
Increase in earth pressure due to inflow of infiltrate due to soil cracks frozen during the thawing season
Insufficient compaction of the ground under the retaining wall
Cracks and damages due to poor placement management
|  | Collapse of the slope at the top of the shaft | Inappropriate shaft type or location
Installation of pit doors on steep slopes or large-cut slopes
Insufficient shaft drainage treatment
|  | ganglion mutation occurs | The shaft part is installed on a slope on one side to generate flat soil pressure

## Shaft part
Work type (WBS) | Risk specifics | Risk | Risk factor
Shaft part (Shaft slope) | Construction | Fall | Joint horizontal to the excavation direction of the rock mass of the tunnel shaft
Risk of fall and collapse when working without shaft slope reinforcement
Risk of rock fall and collision due to insufficient pumice stone arrangement on the upper slope of the shaft
|  | shaft damage | rockfall, avalanche
|  | shaft slope collapse | Poor slope protection
topography
Failure to select an appropriate construction method to secure slope stability
The ground on the shaft slope is different from the design
Slope reinforcement not implemented after shaft part installation
Stability not reviewed when cutting slope, inappropriate selection of reinforcement type according to review
Improper shaft location (valley, piled soil layer, etc.)
Slope collapse due to inflow of large amount of surface water due to occurrence of concentrated lake
Slope collapse due to ground weakening caused by rain in the rainy season
Shaft part (shaft part temporary facility) | Construction | deformation and collapse | Exceeding measurement management standard
step-by-step overexcavation
Lack of earth anchor fixing effect
Use of defective materials (deformed oral materials, etc.)
back ground tensile crack

## Auxiliary Facilities
Work type (WBS) | Risk specifics | Risk | Risk factor
Auxiliary facilities | Construction | Intensification of cracks due to gaps at the top of the lining | Influence of load on lining ceiling facilities (signs, jet fans)
| Management | Poor air quality inside the tunnel | Air supply system centered on dead surface
|  | Noise complaints and air delays | After the tunnel shaft is formed, it is impossible to install soundproof doors until a certain section is entered.
|  | water pollution | After tunnel opening, it is necessary to reduce PH for a certain period, but it is reflected in the design only during the excavation period, and facilities that can reduce PH for other periods are not reflected in the design.
Wall washing water generated during wall washing in the tunnel should be separated and treated separately, but in many cases it is not reflected in the design
| Safety | electric shock | Insufficient distribution box management during electrical construction
|  | safety accidents | Inadequate management of electrical facilities in tunnels
|  | (electric shock, fire, dust, fumes) | Inadequate installation of ventilation facilities in tunnels
|  | suffocation accident | Insufficient ventilation during use of chemicals in confined spaces
|  | fire | Fire caused by sparks during welding/cutting work during miscellaneous steel construction

## Instrumentation
Work type (WBS) | Risk specifics | risk | risk factor
Instrumentation | Construction | Accidents such as cracks and collapses | No risk factors found
Lack of reliability in measured values
Displacement error occurs due to not conducting initial measurement after installation
|  | Displacement of support material | Metrology Measurement Timing and Analytical Errors
delayed reporting
| Management | Process disruptions and air delays due to inefficient responses | Omission of report in case of abnormality
Abnormal data (measurement error)
Time to respond
Non-convergence of measured values (continuous increase)
| Safety | suffocation accident | Asphyxiation by carbon monoxide (CO) generated during equipment operation
|  | fall accident | Accident due to fall during Face-Mapping
|  | fall/fall | Fall/fall due to not wearing PPE during the installation of the instrument at the top of the tunnel
|  | Confinement/collision with equipment | Work zone not set during vibration/noise measurement
|  | Occurrence of safety accident (fall, electric shock, hit) | Fall accident during facemapping
Safety accidents caused by gas, etc.
Safety accidents due to poor illumination
Heavy equipment hit accident during installation and measurement
Fall accidents during high-altitude installation work
| Technical | Impossible to measure due to instrument damage | Impact such as blasting or shotcrete pouring
Damage caused by underground construction equipment, etc.
sudden load increase
Buried sensors and measurement lines when placing shotcrete
Deformation of instruments due to blasting
Instrument damage due to blasting in the tunnel

## Steel pipe multi-stage grouting
Work type (WBS) | Risk specifics | Risk | Risk factor
Auxiliary method (steel pipe multi-stage grouting) | Construction | Collision caused by vibration of the grouting injection pipe and pressure delivery pipe | Grouting injection pipe pressure feed pipe clogged
|  | Collapsing wall | Steel pipe insertion and caulking work not carried out immediately after drilling
Groundwater leakage and soil leakage after drilling is completed
|  | Inadequate ground improvement (consolidation of joint surface) due to early hardening of grouting material | Poor mixing of hardener
|  | Drilling slime flows into the steel pipe | Damaged steel pipe inlet bending part
|  | Collapse | Occurrence of fall and overburden
| Management | Material fall | Concerns about worker collision in the event of sliding or falling due to self-weight after inserting multi-stage steel pipe materials
When transporting multi-stage steel pipes, the wire is unbound and falls
Defective hook release device
| Safety | Risk of electric shock | Mixer power supply, short circuit in distribution panel
|  | Safety accident | Fall, collision and stenosis during steel pipe insertion
When inserting a steel pipe after drilling, the pipe is pushed back and there is a risk of hitting workers in the rear
| Technical | Collapsing due to lack of support | Insufficient design length due to poor ground
Grouting pressure not secured due to cracks, etc.
Insufficient order and reinforcement
Lack of required support
|  | Poor grouting strength | Poor grouting mixing ratio
| Design | Waiting cost due to type change | Type change according to tunnel cancer determination
Personnel and equipment input problems when changing the presence or absence of multi-stage steel pipes

## Ground investigation
Work type (WBS) | Risk specifics | Risk | Risk factor
Ground investigation | Technical | Construction cost increase and construction delay due to ground grade (pattern) change | Poor ground investigation due to low-price orders from ground investigation companies
Difficulty drilling in an accurate location due to poor GPS survey reception in mountainous terrain
Estimation analysis after ground investigation of adjacent section due to equipment inaccessibility in mountainous terrain
|  | Increased construction cost and delayed construction due to additional ground investigation | Generation of additional factors reflecting physical exploration
Failure to conduct appropriate surveys according to tunnel types, etc.
Unskilled ground investigation company
Possible existence of vulnerable ground in the survey omission section
Due to poor ground investigation at the time of design, it is different from the result of ground investigation before construction
Failure to conduct ground investigation due to equipment inaccessibility
|  | Increased construction cost and delayed construction due to soft ground | Impossible to reflect design when discontinuous soft ground is created
Different design and construction survey
|  | Groundwater level drop | Insufficient preliminary investigation of groundwater level
Groundwater contamination due to insufficient treatment after boring investigation
|  | Ground disturbance | Excessive survey work due to ground volatility
Groundwater Pollution Through Boring Balls
Inflow of surface/groundwater in the tunnel due to poor quality of closed holes after completion of ground investigation
Settlement due to ground disturbance by drilling water during ground investigation of soft layer